## DR steps
S No | Steps for Selfcare DR Activity | Time | Status
0 | Checking all the Selfcare servers added to NMS or not | Before activity | WIP
1 | Shared all the customer subnet pools from BLR and HYD FW with tech team | Before activity | Completed
2 | If any misses as per tech team, add those in the BLR FW | Before activity | yet to hear from Tech team
3 | Discuss with Selfcare team on adding the replication rule for BLR selfcare project | Before activity
4 | Create a policy similar to Hyd FW allowing all the sources in BLR FW and keep it disabled | Before activity | Completed
5 | Verify all the subnets which are there in policy routes are also present in selfcare portal address group | Before activity
S No | During DR day, 28th Nov'2023 early morning
1 | Once app team confirms about selfcare bringing down in hyd, disable public policy in the Hyd FW(Policy ID = 275 ) | 12:30am
2 | Once application is stopped, make the domain name changes in the public dns for all the 3 domains | 12:30am
3 | enable public policy in the BLR FW(Policy ID = 1359) post application team confirmation
4 | Once application is live at BLR, check the kubernetes cluster status 1. check this url for node and cluster status - check grafana url - http://172.23.24.145:32099/d/YKnCFW7Ik/kubernetes-cluster-monitoring-via-prometheus?orgId=1&refresh=10s 2. Check K8s master cli for all pods running status - kubectl get pod -n selfcare
5 | Check the HA proxy URL for the session on worker nodes - http://172.23.25.210:9000/stats
6 | Check the server utilization on NMS,
7
http://172.23.25.210:9000/stats
source int - ASR, sources - customer pools and everything else

## persons involved
During DR | Activity
Raj | Connectivity
Harsha | K8s cluster
Abhilash | WAF
28th Daytime
Sathya | WAF/ Networking
Rudra | Networking
Ganesh, Balaji | DB and Angular nodes' load

## HYD DC
SL NO | Application | Per Node vCPU | Per Node Memory | Per Node HDD | Comment | VM Ips | Status
1 | Prod_Angular1 | 8 | 16 | 300 | 200 GB for /app and 100 GB for OS partition | 10.100.112.129
2 | Prod_Angular2 | 8 | 16 | 300 | 200 GB for /app and 100 GB for OS partition | 10.100.112.130
2 | Prod_Angular3 | 8 | 16 | 300 | 200 GB for /app and 100 GB for OS partition | 10.100.112.234 | Not in prod
3 | Prod_k8sMaster1 | 8 | 16 | 300 | 200 GB for /app and 100 GB for OS partition | 10.100.104.61
4 | Prod_k8sMaster2 | 8 | 16 | 300 | 200 GB for /app and 100 GB for OS partition | 10.100.104.63
5 | Prod_k8sMaster3 | 8 | 16 | 300 | 200 GB for /app and 100 GB for OS partition | 10.100.104.73
6 | Prod_k8sWorker1 | 8 | 16 | 400 | 300 GB for /app and 100 GB for OS partition | 10.100.104.81
7 | Prod_k8sWorker2 | 8 | 16 | 400 | 300 GB for /app and 100 GB for OS partition | 10.100.104.85
8 | Prod_k8sWorker3 | 8 | 16 | 400 | 300 GB for /app and 100 GB for OS partition | 10.100.104.87
9 | Prod_k8sWorker4 | 8 | 16 | 400 | 300 GB for /app and 100 GB for OS partition | 10.100.104.89
10 | Prod_k8sWorker5 | 8 | 16 | 400 | 300 GB for /app and 100 GB for OS partition | 10.100.104.9 | Not in prod
11 | Prod_Zabbix1 | 8 | 16 | 300 | 200 GB for /app and 100 GB for OS partition | 10.100.104.90
12 | Prod_Zabbix2 | 8 | 16 | 300 | 200 GB for /app and 100 GB for OS partition | 10.100.104.98
13 | HA Proxy servers | 8 | 16 | 200 |  | 10.100.104.136
14 | HA Proxy servers | 8 | 16 | 200 |  | 10.100.104.137
| DB master |  |  |  |  | 10.100.104.23
| DB Slave |  |  |  |  | 10.100.104.50
| prodharbor | 10.100.112.93 | 4 | 4 | 300 | Ubuntu-20.04 | 10.100.116.121 | SGH128V9B5

## BLR servers
SL No | Application | Per node vCPU | Per node Memory | Per node HDD | VM Ips | ESXi | VIP | Passwords | NMS Status | SSL | Status
1 | DR_Angular1 | 8 vCPUs | 16 GB | 300 GB | 172.23.21.157 | 172.23.25.197 | 172.30.30.21 - On Radware WAF | Dr_@n<gUl>R1 | Completed | Need to update | Normal
2 | Dr_Angular2 | 8 vCPUs | 16 GB | 300 GB | 172.23.21.158 | 172.23.25.196 |  | Dr_@n<gUl>R2 | Completed | Need to update | Normal
3 | Dr_k8sMaster1 | 8 vCPUs | 16 GB | 300 GB | 172.23.24.145 | 172.23.25.197 |  | DrK@sM@$ter1 | Completed |  | Normal
4 | Dr_k8sMaster2 | 8 vCPUs | 16 GB | 300 GB | 172.23.24.141 | 172.23.25.196 |  | DrK@sM@$ter2 | Completed |  | Normal
5 | DR_k8smaster3 | 8 vCPUs | 16 GB | 300 GB | 172.23.24.125 | 172.23.25.196 |  | dF#5WaX24 | Completed |  | Abnormal, Process killed , dcsupport disabled
6 | DR_k8sWorker1 | 8 vCPUs | 16 GB | 400 GB | 172.23.24.126 | 172.23.25.196 |  | 0w^0BS&l7 | Completed |  | Normal
7 | DR_k8sWorker2 | 8 vCPUs | 16 GB | 300 GB | 172.23.24.99 | 172.23.25.196 |  | 83$$!dadEA | Completed |  | Power off
8 | DR_k8sWorker3 | 8 vCPUs | 16 GB | 400 GB | 172.23.24.178 | 172.23.25.197 |  | drk8sworker3#Act | Completed |  | Normal
9 | DR_k8sWorker4 | 8 vCPUs | 16 GB | 400 GB | 172.23.24.84 | 172.23.25.197 |  | drk8sworker4#Act | Completed |  | Normal
10 | dr_Zabbix2 | 8 vCPUs | 16 GB | 300 GB | 172.23.24.144 | 172.23.25.196 |  | DR_Z@bb!x2 | Completed |  | Normal (single bad attempts)
11 | DR_Zabbix1 | 8 vCPUs | 16 GB | 300 GB | 172.23.24.89 | 172.23.25.196 |  | dcsupport user | Completed
12 | HA proxy 1 | 8 vCPUs | 16 GB | 200 GB | 172.23.25.245 | 172.23.25.196 | 172.23.25.210-HA Proxy | dcsupport user | Completed
13 | HA proxy 2 | 8 vCPUs | 16 GB | 200 GB | 172.23.25.246 | 172.23.25.197 |  | dcsupport user | Completed
14 | DR harbor |  |  |  | 172.23.21.36 |  |  | root@123 | Completed | Need to update | Normal
15 | DB |  |  |  | 172.23.26.39 | vxrail |  | Blr@Selfc@reDB | Completed |  | Normal

## domain
Application | BLR Public IP | BLR A Record | HYD Public IP | HYD A Record | CNAME Record | Currently Pointed to | CNAME Pointing to change during DR | On DDOS | Action to be taken from
api gateway | 172.23.25.210 | selfcareprod-apigateway-blr.actcorp.in | 10.100.104.135 | selfcareprod-apigateway-hyd.actcorp.in | Selfcareprod-apigateway.actcorp.in | selfcareprod-apigateway-hyd.actcorp.in | selfcareprod-apigateway-blr.actcorp.in | No | Tech team
harbor | 172.23.21.36 | harbor-blr.actcorp.in | 10.100.112.93 | harbor-hyd.actcorp.in | harbor.actcorp.in | harbor-hyd.actcorp.in | harbor-blr.actcorp.in | No | Tech team
selfcare | 106.51.41.221 | selfcare-blr.actcorp.in | 202.53.8.130 | selfcare-hyd.actcorp.in | selfcare.actcorp.in | selfcare-hyd.actcorp.in | selfcare-blr.actcorp.in | No | Tech team

## connectivity
Application Name | DC_Application_IP | DR_Application_IP | Location site - DC |  |  |  |  | Location site - DR
|  |  | Target App | Target IP | Target port | Location | URL | Target IP | Target port
NEW Selfcare |  | 172.23.24.126 172.23.24.99 172.23.24.178 172.23.24.84 | AAA STL | http://stlmw.actcorp.net | 10091 |  | http://stlmw.actcorp.net:10091/new-api/QodServices?wsdl | http://stlmw.actcorp.net | 10091
| 10.100.104.81 |  |  | http://stlmw.actcorp.net | 7876 |  | http://stlmw.actcorp.net:7876/policydesigner/services/SubscriptionService?wsdl | http://stlmw.actcorp.net | 7876
| 10.100.104.85 | [5 empty] | http://stlmw.actcorp.net:7876/policydesigner/services/SessionManagementService?wsdl
| 10.100.104.87 |  | AAA ALEPO | http://172.23.25.70 | 8280 |  | http://172.23.25.70:8280/services/ACT-Alepo-Service-NewAPI/QodOperationsService?wsdl | http://172.23.25.70 | 8280
| 10.100.104.89 | [5 empty] | http://172.23.25.70:8280/services/ACT-Alepo-Service-VasAPI/SubscriptionService?wsdl |  |  | http://172.23.25.70:8280/services/ACT-Alepo-Service-VasAPI/SubscriptionService?wsdl
[7 empty] | http://172.23.25.70:8280/services/ACT-Alepo-Service-VasAPI/SessionManagementWS?wsdl |  |  | http://172.23.25.70:8280/services/ACT-Alepo-Service-VasAPI/SessionManagementWS?wsdl
|  |  | ESB URL | http://esb9025.actcorp.net | 9025 |  | http://esb9025.actcorp.net:9025/rest/act/sales/getSubscriberInfo | http://esb9025.actcorp.net | 9025 | http://esb9025.actcorp.net:9025/rest/act/sales/getSubscriberInfo
[7 empty] | http://esb9025.actcorp.net:9025/rest/act/sales/getSubMultipleInfo |  |  | http://esb9025.actcorp.net:9025/rest/act/sales/getSubMultipleInfo
|  |  |  | http://esb9037.actcorp.net | 9037 |  | http://esb9037.actcorp.net:9037/makePayment | http://esb9037.actcorp.net:9037/makePayment | 9037 | http://esb9037.actcorp.net:9037/makePayment
|  |  |  | http://esb9030.actcorp.net | 9030 |  | http://esb9030.actcorp.net:9030/esb/services/getAgreementInfo | http://esb9030.actcorp.net:9030/esb/services/getAgreementInfo | 9030 | http://esb9030.actcorp.net:9030/esb/services/getAgreementInfo
[7 empty] | http://esb9030.actcorp.net:9030/getAcctBillsFromIT |  |  | http://esb9030.actcorp.net:9030/getAcctBillsFromIT
[7 empty] | http://esb9030.actcorp.net:9030/getPaymentInfoFromIT |  |  | http://esb9030.actcorp.net:9030/getPaymentInfoFromIT
[7 empty] | http://esb9030.actcorp.net:9030/GetSubscriberTickets |  |  | http://esb9030.actcorp.net:9030/GetSubscriberTickets
|  |  |  | http://esb9031.actcorp.net | 9031 |  | http://esb9031.actcorp.net:9031/modifySubscriber | http://esb9031.actcorp.net:9031/modifySubscriber | 9031 | http://esb9031.actcorp.net:9031/modifySubscriber
|  |  |  | http://esb9023.actcorp.net | 9023 |  | http://esb9023.actcorp.net:9023/rest/act/sales/changePwd | http://esb9023.actcorp.net:9023/rest/act/sales/changePwd | 9023 | http://esb9023.actcorp.net:9023/rest/act/sales/changePwd
|  |  |  | http://esb9000.actcorp.net | 9000 |  | http://esb9000.actcorp.net:9000/getFinancialSummary | http://esb9000.actcorp.net:9000/getFinancialSummary | 9000 | http://esb9000.actcorp.net:9000/getFinancialSummary
[7 empty] | http://esb9000.actcorp.net:9000/esb/services/cxf/GetDMSInvoiceLink |  |  | http://esb9000.actcorp.net:9000/esb/services/cxf/GetDMSInvoiceLink
|  |  |  | http://esb9007.actcorp.net | 9007 |  | http://esb9007.actcorp.net:9007/postCreditDebit | http://esb9007.actcorp.net:9007/postCreditDebit | 9007 | http://esb9007.actcorp.net:9007/postCreditDebit
|  |  | FTP Server for GST upload | 10.100.104.161 | 21 |  | 10.100.104.161 | 10.100.104.161 | 21 | 10.100.104.161
|  |  | Upgrade Plan URL | https://myfibernet.actcorp.in | 443 |  | https://myfibernet.actcorp.in/ftupgrade/#/login | https://myfibernet.actcorp.in | 443 | https://myfibernet.actcorp.in/ftupgrade/#/login
|  |  | Chatbot URL | https://act-corp.rezo.ai/index.php | 443 |  | https://act-corp.rezo.ai/index.php | https://act-corp.rezo.ai/index.php | 443 | https://act-corp.rezo.ai/index.php
|  |  | Access to DMS Server | https://dms.actcorp.in | 443 |  | https://dms.actcorp.in | https://dms.actcorp.in | 443 | https://dms.actcorp.in
|  |  | PROD MySQL Details | 10.100.104.23 | 3306 |  | 10.100.104.23 | 10.100.104.23 | 3306 | 10.100.104.23
|  |  | CDR - Oracle DB details | 10.100.109.96 | 1521 |  | 10.100.109.96 | 10.100.109.96 | 1521 | 10.100.109.96
|  |  | ExactPay | https://exact.actcorp.in | 443 |  | https://exact.actcorp.in/rest/prospect/checkprospectStatus/ | https://exact.actcorp.in | 443 | https://exact.actcorp.in/rest/prospect/checkprospectStatus/
|  |  | EBExactPay | https://ebexactapp.actcorp.in | 443 |  | https://ebexactapp.actcorp.in/api/prospect/get-prospect-details | https://ebexactapp.actcorp.in | 443 | https://ebexactapp.actcorp.in/api/prospect/get-prospect-details
|  |  | SMTP/SMS | 10.100.112.157 | 587 |  | 10.100.112.157 | 10.100.112.157 | 587 | 10.100.112.157
|  |  |  | https://www.smsstriker.com | 443 |  | https://www.smsstriker.com/API/sms.php | https://www.smsstriker.com | 443 | https://www.smsstriker.com/API/sms.php
|  |  | VAS APIs | 10.100.104.67 | 8330 |  | 10.100.104.67:8330/actcfcommonservices-portlet/cfcommonrest/actvas/activate | 10.100.104.67 | 8330 | 10.100.104.67:8330/actcfcommonservices-portlet/cfcommonrest/actvas/activate
[7 empty] | http://10.100.104.67:8330/actcfcommonservices-portlet/cfcommonrest/actdeactivatevas/deactivate |  |  | http://10.100.104.67:8330/actcfcommonservices-portlet/cfcommonrest/actdeactivatevas/deactivate
|  |  | Referral (CRP) APIs | https://myfibernet.actcorp.in | 443 |  | https://myfibernet.actcorp.in/api/crp/crp_add | https://myfibernet.actcorp.in | 443 | https://myfibernet.actcorp.in/api/crp/crp_add
[7 empty] | https://myfibernet.actcorp.in/api/crp/getcrp_ref |  |  | https://myfibernet.actcorp.in/api/crp/getcrp_ref
[7 empty] | https://myfibernet.actcorp.in/api/crp/getcrp_offers |  |  | https://myfibernet.actcorp.in/api/crp/getcrp_offers
[7 empty] | https://myfibernet.actcorp.in/api/crp/getcrp_Rewards |  |  | https://myfibernet.actcorp.in/api/crp/getcrp_Rewards
|  |  | ITP Payments - Digital Payment | http://10.100.112.123 | 80 |  | http://10.100.112.123/index.php/api_validation/thirdparty_api_validation | http://10.100.112.123 | 80 | http://10.100.112.123/index.php/api_validation/thirdparty_api_validation
[7 empty] | http://10.100.112.123/index.php/customerpayment/getcustomerdetailsSMSpayment |  |  | http://10.100.112.123/index.php/customerpayment/getcustomerdetailsSMSpayment
[7 empty] | http://10.100.112.123/index.php/customerpayment/updatecustomerpayment |  |  | http://10.100.112.123/index.php/customerpayment/updatecustomerpayment
|  |  | Whatsapp Integration | soa.actcorp.in | 9091 |  | https://soa.actcorp.in:9091/actwhatsappservice/whatsappRegistration (Basic YWN0d2hhdHNhcHB1c2VyOkBiZ21zbnJyc25nS3NVaGFA) | soa.actcorp.in | 9091 | https://soa.actcorp.in:9091/actwhatsappservice/whatsappRegistration (Basic YWN0d2hhdHNhcHB1c2VyOkBiZ21zbnJyc25nS3NVaGFA)
|  |  | Invoice Service | http://172.23.25.146 | 5000 |  | http://172.23.25.146:5000/send/invoiceurl | http://172.23.25.146 | 5000 | http://172.23.25.146:5000/send/invoiceurl
|  |  | BOLGS | https://www.actcorp.in | 443 |  | https://www.actcorp.in/selfcare-blog-details | https://www.actcorp.in | 443 | https://www.actcorp.in/selfcare-blog-details